## Decision & Approval Matrix
Decision & Approval Matrix
PMU-ADM-360-MASTER-20261022 · Prepared for Management Review · Not an approval, publication confirmation or closure certificate
ID | Matter to decide | Question & interpretation | Linked severity | Evidence (findings) | Risk if unresolved | Options | Professional recommendation | Reference requiring approval | Decision authority | Mr. Radhi's role | Implementation | Publication verification | Status | Approval reference / date | Follow-up date
D-01 | Application fees, VAT basis and test fees | Which application fee applies to each applicant category (international transfer/visiting, Medicine, undergraduate, graduate), on what VAT basis and from which effective date? What is the current Aptis (and retake) fee? | P0 2 · P1 1 | F-039, F-052, F-026, F-036, F-119, F-104, F-105, F-108, F-111 | Applicants may pay or budget for the wrong fee; refunds, complaints and reputational risk. | A. Adopt the official Other Fees schedule as the single source and link all pages to it; B. Confirm category-specific exceptions in writing and publish them in the schedule. | Option A: Financial Affairs confirms one dated fee schedule by applicant category (with VAT basis); all admissions pages link to it instead of restating amounts. | Approved, dated fee schedule 2026/2027 by applicant category, with VAT basis and effective date | Financial Affairs (fee authority) | REFER | Website content publisher — OWNER_TO_CONFIRM | Admissions Office (read-back) | PENDING — NOT APPROVED |  | To be set on management direction
D-02 | Current admission cycle, calendar and application channels | Is an admission cycle currently open (e.g. Spring 2027)? Which dates, channels (Qabool, Study in Saudi, PMU portal) and orientation date apply, and what should be shown while no cycle is open? | P0 1 · P1 4 | F-014, F-015, F-005, F-030, F-041, F-053, F-016 | Applicants act on expired dates or cannot tell whether admission is open. | A. Publish the next cycle with dates; B. Publish an interim notice stating that applications are closed and when the next cycle opens. | Option B immediately (dated interim notice), then Option A when next-cycle dates are approved. | Approved admission calendar for the next cycle; channel per applicant category | Deanship of Enrollment and Registration / Admissions (academic calendar: Registrar) | DIRECT (interim notice) · REFER (calendar) | Admissions Office + publisher | Admissions Office | PENDING — NOT APPROVED |  | To be set on management direction
D-03 | Undergraduate eligibility, test equivalences and weightings | Confirm for each applicant category: accepted tests (SAT I/II, Tahseely, IELTS, TOEFL), minimum scores, SAT 1 (1200) substitution rules, minimum weighted totals (including the values requested on 26 Oct 2025), identity documents and attestation authority. | P0 1 · P1 7 | F-040, F-023, F-024, F-025, F-027, F-042, F-054, F-059, F-060, F-071, F-070, F-117, F-124, F-065, F-067, F-061, F-029, F-050 | Inconsistent eligibility decisions and applicant disputes; discontinued SAT II still required. | A. One approved undergraduate admission matrix referenced by all pages; B. Page-by-page correction after written confirmation. | Option A: one approved undergraduate admission matrix (tests, minimums, weights, substitutions, documents), referenced by every page. | Approved undergraduate admission criteria (incl. minimum weighted totals requested on 26 Oct 2025) | Competent academic authority (colleges / academic council) with Admissions | REFER (values) · DIRECT (page alignment) | Admissions Office + publisher | Admissions Office | PENDING — NOT APPROVED |  | To be set on management direction
D-04 | Graduate eligibility and English-language requirements | Which IELTS/TOEFL thresholds govern each graduate programme (6.0 vs 6.5; EMGMS 7), which GPA rules apply (PhD BA 2.80/3.00/3.20; "Very Good"), and which programme-specific conditions (work experience, written test, duration) are current? | P0 0 · P1 5 | F-073, F-100, F-097, F-077, F-084, F-087, F-099, F-092, F-095, F-101, F-089 | Applicants judged against different English and GPA thresholds for the same programme; another university’s text on a PMU page. | A. Approved graduate entry matrix by programme; B. Remove non-PMU text (EMGMS) immediately and confirm values afterwards. | Remove the non-PMU (UA CESL) text now; then Option A: an approved graduate entry matrix by programme. | Approved graduate admission requirements per programme (English thresholds, GPA rules, special conditions) | Graduate studies authority / programme councils | DIRECT (removal request) · REFER (values) | Programme owners + publisher | Admissions Office | PENDING — NOT APPROVED |  | To be set on management direction
D-05 | Programme portfolio and official names | Which programmes are currently open for admission (including B.S. Chemical Engineering, EMGMS, the Master of Engineering in Innovation, Sustainability and Entrepreneurship, Medicine), and what are their official names and abbreviations? | P0 0 · P1 2 | F-012, F-043, F-048, F-074, F-106, F-094, F-083 | Applicants cannot reliably tell which programmes are open; programmes priced without an application route. | A. Publish one authoritative programme list used by all admission pages; B. Mark programmes not open for admission. | Option A: one authoritative list of programmes open for admission, with official names and abbreviations. | Official list of programmes open for admission (academic affairs) | Academic affairs / colleges | REFER | Admissions Office + publisher | Admissions Office | PENDING — NOT APPROVED |  | To be set on management direction
D-06 | Legacy guides and linked resources | Should the 2018 Web Admission Guide and the 2017 Aptis guide be withdrawn, replaced or archived, and who restores or removes the broken scholarship links? | P0 0 · P1 2 | F-036, F-121, F-035 | The 2018 guide contradicts current fees and procedures; broken scholarship links. | A. Withdraw now and replace later; B. Replace before withdrawal; C. Archive with a dated "historical" label. | Option A: withdraw the 2018 guide now and replace it later; restore or remove the three 404 links. | Not required for withdrawal; replacement guide requires Admissions approval | Admissions Office | DIRECT | Website content publisher — OWNER_TO_CONFIRM | Admissions Office | PENDING — NOT APPROVED |  | To be set on management direction
D-07 | Contact channels and enquiry-form privacy | Which official Admissions contact details (email, telephone, hours) should be published, and which privacy notice applies to the Admission Query form and the portal? | P0 0 · P1 1 | F-002, F-020, F-034, F-044, F-110, F-031 | Applicants cannot reach Admissions directly; personal data collected without a visible privacy notice. | A. Publish an official Admissions contact block on every admissions page; B. Link the university privacy notice from forms. | Publish an official Admissions contact block; link the university privacy notice from the enquiry form (privacy wording owner to be confirmed). | Official Admissions contact details; university privacy notice | Admissions Office (contacts) · OWNER_TO_CONFIRM (privacy notice) | DIRECT (contacts) · REFER (privacy) | Admissions Office + publisher | Admissions Office | PENDING — NOT APPROVED |  | To be set on management direction
D-08 | Content ownership, review cycle and single source of truth | Who is the accountable owner and approver for each admissions page, what review cycle applies (e.g. before each cycle opens), and should pages display a "last reviewed" date? | P0 0 · P1 0 |  | Without named owners and a review cycle, the same defects will recur each admission cycle. | A. Named owner per page plus a pre-cycle review; B. Central editor with owner sign-off. | Option A: a named owner per page, a review before each cycle opens, and a visible "last reviewed" date. | Content ownership register approved by Admissions leadership | Admissions leadership | DIRECT | Admissions Office | Admissions leadership | PENDING — NOT APPROVED |  | To be set on management direction
D-09 | Approval of ready editorial corrections | May the 48 editorial corrections (Annex sheet) and the editorial findings be implemented directly, given that none changes a value or requirement? | P0 0 · P1 0 | 35 editorial findings + 48 corrections | Low-impact errors persist and reduce credibility. | A. Approve as a batch; B. Approve page by page. | Option A: approve the 48 editorial corrections as a batch (none changes a value or requirement). | Not required (no policy content) | Admissions Office (content approver) | DIRECT | Website content publisher — OWNER_TO_CONFIRM | Admissions Office | PENDING — NOT APPROVED |  | To be set on management direction
D-10 | Accessibility and technical publishing baseline | Should admissions pages meet a stated accessibility baseline (e.g. WCAG 2.1 AA: language attribute, image alternatives, landmarks, mobile reflow) and secure links? | P0 0 · P1 0 | F-003, F-004, F-008, F-069, F-009, F-131 | Pages are harder to use with assistive technology and on mobile; one portal link uses http. | A. Adopt WCAG 2.1 AA for admissions pages; B. Address listed items only. | Option B now (fix listed items); consider Option A (WCAG 2.1 AA baseline) with the publisher. | University web/accessibility standard (if any) — OWNER_TO_CONFIRM | Website publisher / IT — OWNER_TO_CONFIRM | REFER | Website publisher / IT — OWNER_TO_CONFIRM | Admissions Office | PENDING — NOT APPROVED |  | To be set on management direction

## Corrective Action Roadmap
Corrective Action Roadmap / Tracker
Lifecycle after authorisation: APPROVE → IMPLEMENT → SAVE → REOPEN → READ BACK → COMPARE → VERIFY → CLOSE. Target dates are proposals, not commitments.
Action | Priority | 1. Proven problem | 2. Required outcome | 3. Proposed text / action | 4. Decision pending | 5. Implementation owner | 6. Prior approval | 7. Proposed target | 8. Status | 9. Implementation & publication evidence | 10. Re-verification result | Indicator
A-01 | P0 | No current admission cycle visible (F-014, F-015, F-030, F-005) | Applicants see a dated statement of the current cycle status | Dated notice on root page and Admissions Calendar; fix footer calendar link | D-02 | Admissions Office | None for an interim notice; calendar approval for dates | Immediately after direction (proposed, non-binding) | NOT_STARTED |  |  | Notice visible on both pages; dated
A-02 | P0 | Conflicting application fees (F-039, F-052, F-026) | One fee per category, one VAT basis, everywhere | Replace restated amounts with a link to the approved schedule | D-01 | Admissions Office + Financial Affairs | Financial Affairs confirmation | After D-01 (proposed, non-binding) | NOT_STARTED |  |  | Zero conflicting fee statements on re-read
A-03 | P0 | Discontinued SAT II required (F-040) | No discontinued test is required | Remove SAT II or replace with the approved alternative | D-03 | Admissions Office + colleges | Academic authority confirmation of the alternative | After D-03 (proposed, non-binding) | NOT_STARTED |  |  | Requirement aligned on all pages
A-04 | P1 | Another university’s text on EMGMS page (F-097) | Page contains PMU-only, approved requirements | Remove UA CESL text; publish confirmed thresholds | D-04 | Graduate programme owner + Admissions | Programme owner confirmation | Removal immediately; values after D-04 (proposed, non-binding) | NOT_STARTED |  |  | Text removed; threshold confirmed
A-05 | P1 | Graduate English thresholds conflict (F-073, F-100) | Forms and programme pages state the same approved thresholds | Align generic form and programme pages to the approved matrix | D-04 | Graduate programme owners | Graduate authority approval | After D-04 (proposed, non-binding) | NOT_STARTED |  |  | Form and programme pages match
A-06 | P1 | Undergraduate criteria inconsistent (F-024, F-059, F-070, F-117 …) | One approved matrix referenced by all pages | Publish matrix; align pages | D-03 | Admissions Office + colleges | Academic authority approval | Before next cycle opens (proposed, non-binding) | NOT_STARTED |  |  | All undergraduate pages reference the matrix
A-07 | P1 | Outdated guide and broken links (F-036, F-121, F-035) | No outdated guide or 404 link in the section | Withdraw/replace guides; fix links | D-06 | Admissions Office + publisher | Admissions direction | Immediately after direction (proposed, non-binding) | NOT_STARTED |  |  | No 404 links; guide current or withdrawn
A-08 | P1 | Programme lists inconsistent (F-012, F-043, F-048, F-074) | One authoritative programme list | Publish list; align pages and names | D-05 | Admissions Office + programme owners | Academic affairs confirmation | Before next cycle opens (proposed, non-binding) | NOT_STARTED |  |  | Lists identical across pages
A-09 | P1 | No Admissions contact; no privacy notice (F-002, F-020, F-034) | Official contacts and privacy link visible | Add contact block; link privacy notice | D-07 | Admissions Office | Admissions; privacy owner to confirm | After D-07 (proposed, non-binding) | NOT_STARTED |  |  | Contact block and privacy link present
A-10 | P2 | Editorial errors (48 corrections + editorial findings) | Corrected text on all affected pages | Apply the 48 approved before/after corrections | D-09 | Admissions content editor + publisher | Admissions content approval | After D-09 (proposed, non-binding) | NOT_STARTED |  |  | Each corrected occurrence re-read and logged
A-11 | P2 | Accessibility and link-protocol items (F-003, F-004, F-008, F-069, F-131) | Listed items pass a re-check | Fix lang attribute, alt text, landmarks, reflow, https link | D-10 | Publisher / IT | Publisher/IT agreement | After D-10 (proposed, non-binding) | NOT_STARTED |  |  | Automated re-check passes for listed items
A-12 | P2 | No named owners or review cycle | Owner register and pre-cycle review in place | Approve owner register; show "last reviewed" dates | D-08 | Admissions leadership | Admissions leadership | Before next cycle opens (proposed, non-binding) | NOT_STARTED |  |  | Owner register approved; dates visible
A-13 | P3 | No applicant feedback evidence | Evidence base for future reviews | Approve survey/enquiry-log design before any collection | D-08 | Admissions Office (owner to be confirmed) | Separate authorisation + privacy review | To be set (proposed, non-binding) | NOT_STARTED |  |  | Survey approved before any data collection

## Priority Findings
Priority findings (P0–P1)
PMU-ADM-360-MASTER-20261022 · Prepared for Management Review · Not an approval, publication confirmation or closure certificate
ID | P | Finding | Page | Classification | Impact | Resolution status | Decision | Owner | Last verified
F-005 | P1 | Footer "Academic Calendar" link opens the 2021/2022 calendar | Admissions Office | Outdated or expired content | Applicant · Operational | ESCALATION REQUIRED | D-02 | Website content publisher | 2026-10-22
F-012 | P1 | Programme lists incomplete and inconsistent across admissions pages | Degrees & Programs | Conflict between two or more sources | Applicant · Financial | OPEN CONFLICT | D-05 | Academic programme owners + Admissions Office | 2026-10-21
F-014 | P0 | Admissions calendar shows only an expired cycle | Admissions Calendar | Outdated or expired content | Applicant · Academic | ESCALATION REQUIRED | D-02 | Admissions Office | 2026-10-22
F-020 | P1 | Admission Query form lacks privacy notice and alternative contacts | Admission Query | Missing information important to applicants | Applicant · Operational | ESCALATION REQUIRED | D-07 | Admissions Office + Legal/Compliance unit | 2026-10-21
F-023 | P1 | Undergraduate admission requirements hidden by immediate redirect | apply | Missing information important to applicants | Applicant · Academic | ESCALATION REQUIRED | D-03 | Admissions Office | 2026-10-21
F-024 | P1 | Conflicting descriptions of the SAT 1 (1200) alternative | apply | Conflict between two or more sources | Applicant · Academic | OPEN CONFLICT | D-03 | Admissions Office | 2026-10-21
F-030 | P1 | Application portal and website calendar present conflicting information | welcome | Conflict between two or more sources | Applicant · Operational | OPEN CONFLICT | D-02 | Admissions Office | 2026-10-21
F-035 | P1 | Broken scholarship and GPA-calculator links in the side menu | Admissions side menu (shared) | Verified error in published information | Applicant · Academic | OPEN | D-06 | OWNER_TO_CONFIRM | 2026-10-22
F-036 | P1 | Linked Web Admission Guide is outdated and conflicts with current fees | Admissions side menu (shared) | Outdated or expired content | Applicant · Financial | ESCALATION REQUIRED | D-01, D-06 | Admissions Office | 2026-10-21
F-039 | P0 | Conflicting application fees for transfer and visiting students | International Students’ Office | Conflict between two or more sources | Applicant · Financial | OPEN CONFLICT | D-01 | Admissions Office + Financial Affairs | 2026-10-22
F-040 | P0 | International freshman criteria require discontinued SAT II test | International Students’ Office | Outdated or expired content | Applicant · Academic | ESCALATION REQUIRED | D-03 | Admissions Office + relevant colleges | 2026-10-22
F-041 | P1 | No published application route or deadline for non-Saudi applicants | International Students’ Office | Missing information important to applicants | Applicant · Operational | ESCALATION REQUIRED | D-02 | Admissions Office | 2026-10-21
F-042 | P1 | Missing SAT minimum and empty Transportation section for international students | International Students’ Office | Missing information important to applicants | Applicant · Academic | ESCALATION REQUIRED | D-03 | Admissions Office | 2026-10-21
F-052 | P0 | Conflicting College of Medicine application fee | Admissions to the College of Medicine | Conflict between two or more sources | Applicant · Financial | OPEN CONFLICT | D-01 | Admissions Office + Financial Affairs + College of Medicine | 2026-10-22
F-053 | P1 | Inconsistent application channel across undergraduate pages | Admissions to the College of Medicine | Ambiguity in procedures or fees | Applicant · Operational | ESCALATION REQUIRED | D-02 | Admissions Office | 2026-10-21
F-054 | P1 | College of Medicine minimum scores inconsistent with weighted-score threshold | Admissions to the College of Medicine | Verified error in published information | Applicant · Academic | OPEN | D-03 | College of Medicine + Admissions Office | 2026-10-21
F-059 | P1 | TOEFL iBT minimum not published on undergraduate admission pages | Direct Admissions from Secondary School | Missing information important to applicants | Applicant · Academic | ESCALATION REQUIRED | D-03 | Admissions Office + Testing Centre | 2026-10-21
F-070 | P1 | Inconsistent list of majors with special admission requirements | Admissions Requirements , Computer Science and Engineering Majors | Conflict between two or more sources | Applicant · Academic | OPEN CONFLICT | D-03 | Admissions Office | 2026-10-21
F-073 | P1 | Conflicting IELTS minimum between application form and programme pages | Graduate Admissions | Conflict between two or more sources | Applicant · Academic | OPEN CONFLICT | D-04 | Graduate programme owner + Admissions | 2026-10-22
F-074 | P1 | Engineering Management Master’s programme listed without an application route | Graduate Admissions | Ambiguity in procedures or fees | Applicant · Financial | ESCALATION REQUIRED | D-05 | Graduate programme owner + Admissions | 2026-10-21
F-084 | P1 | Ambiguous eligibility conditions for the PhD in Business Administration | Admissions Requirements , Admissions to the PhD in Business Administration | Ambiguity in procedures or fees | Applicant · Academic | ESCALATION REQUIRED | D-04 | Graduate programme owner + Admissions | 2026-10-21
F-097 | P1 | Engineering Management requirements page contains another university’s content | Admissions Requirements, Master of Science in Engineering Management (EMGMS) | Verified error in published information | Applicant · Academic | OPEN | D-04 | Graduate programme owner + Admissions | 2026-10-22
F-099 | P1 | Incomplete admission requirements for the International Business Law Master’s | Admissions to the Master of Arts (MA) in International Business Law Program | Missing information important to applicants | Applicant · Academic | ESCALATION REQUIRED | D-04 | Graduate programme owner + Admissions | 2026-10-21
F-100 | P1 | Conflicting IELTS and TOEFL thresholds for the International Business Law MA | Admissions to the Master of Arts (MA) in International Business Law Program | Conflict between two or more sources | Applicant · Academic | OPEN CONFLICT | D-04 | Graduate programme owner (Deanship of Graduate Studies) + Admissions Office | 2026-10-22
F-117 | P1 | Conflicting accepted tests for direct Core Program entry | Aptis Placement Test | Conflict between two or more sources | Applicant · Academic | OPEN CONFLICT | D-03 | Admissions Office | 2026-10-21

## Historical Amendments
Historical Amendment Verification (requests of 26 Oct 2025)
Statuses: PUBLISHED · PARTIALLY_PUBLISHED · NOT_PUBLISHED · SUPERSEDED · CANNOT_VERIFY · NOT_APPLICABLE
ID | Requested amendment | Status | Current published evidence | Decision | Checked | Basis
H-1 | Minimum weighted scores 74% (CS & Engineering) / 72% (non-Engineering) with competitive-minimum and interview note | NOT_PUBLISHED | No "74%" or "72%" appears on any captured page; the CS & Engineering page refers to a "minimum weighted total, defined by the Admissions Office". | D-03 | 2026-10-22 | Historical request (email of 26 Oct 2025); compared with current published content — not treated as approved policy.
H-2 | Addition of B.S. Chemical Engineering | PARTIALLY_PUBLISHED | Listed on Degrees & Programs and the list of majors; absent from the special-requirements majors list on the CS & Engineering requirements page. | D-05 | 2026-10-22 | Historical request (email of 26 Oct 2025); compared with current published content — not treated as approved policy.
H-3 | Application fee SAR 500 → SAR 950 for international, transfer and visiting students | PARTIALLY_PUBLISHED | SAR 950 (incl. VAT) on Transfer and Visiting pages; SAR 500 (excl. VAT) remains on the International Students page. The request specified "excl. VAT"; the official schedule states "includes the VAT 15%". Escalation: the VAT basis of the request conflicts with the published official schedule. | D-01 | 2026-10-22 | Historical request (email of 26 Oct 2025); compared with current published content — not treated as approved policy.
H-4 | Removal of SAAT / SAT 2 requirement for CS & Engineering | PARTIALLY_PUBLISHED | "SAT 2" no longer appears on the CS & Engineering requirements page, but "(SAAT – Tahseely)" is still listed there and "SAT II 30%" remains on the International Students page. The intended scope of the request (removing SAT 2 only, or Tahseely as well) needs confirmation. | D-03 | 2026-10-22 | Historical request (email of 26 Oct 2025); compared with current published content — not treated as approved policy.
H-5 | APTIS retake fee SAR 575 → SAR 950 (VAT) | NOT_PUBLISHED | "APTIS Exam Fees SAR 575" on the Other Fees page. | D-01 | 2026-10-22 | Historical request (email of 26 Oct 2025); compared with current published content — not treated as approved policy.
H-6 | Revision of the Web Admission Guide | NOT_PUBLISHED | The linked guide is unchanged (MD5-identical to 11 Oct 2026; dated December 2018; p. 20 states SR 500). | D-06 | 2026-10-22 | Historical request (email of 26 Oct 2025); compared with current published content — not treated as approved policy.

## Gaps & Residual Risks
Gaps, exceptions and residual risks
PMU-ADM-360-MASTER-20261022 · Prepared for Management Review · Not an approval, publication confirmation or closure certificate
Gap / exception | Count | Residual risk | Route
Open conflicts awaiting institutional confirmation | 14 | Applicants may receive contradictory requirements or fees | D-01 … D-05
Items blocked from verification (F-033, F-131) | 2 | Possible spelling errors / failing http link remain unconfirmed | Manual check from a public browser
No approved policy references available to the review | — | Values cannot be confirmed as correct, only as conflicting | D-01 … D-05
No applicant data or feedback | — | Experience findings are content-based | A-13
Operational application of procedures not verified | — | Report does not state how procedures are applied | D-01 … D-04
No correction published yet | 130 | All P0 risks remain live on 22 Oct 2026 | A-01 … A-13
Exclusions by mandate (portal login, forms, security/performance testing, applicant records) | — | Not assessed | —