## Summary
Admission Pages Comments Register
Revisit of the Admissions Office webpages – published content as of 10 October 2026
Reference: thread "comments on Admission pages" ¦ Prepared by: Nader Alfarhan, Student Affairs ¦ Read-only review
Comments by priority
Scope | P1 | P2 | P3 | Total
Pages linked from the Admissions page | 6 | 29 | 16
Legacy pages (not linked from the hub) | 2 | 5 | 3
Total
Overall status
NOT READY FOR CLOSURE
Ten items require a documented decision by the policy / fee owner before wording can be corrected.
Priority legend
P1 | High – affects eligibility, fees or the application route
P2 | Medium – inconsistency or missing information
P3 | Low – wording, accessibility or housekeeping
Sheets
• Comments – page-by-page comments with verbatim evidence and proposed change
• Decisions – items requiring an owner decision
• Previous requests – live status of amendments requested in the thread
Limits: desktop view not tested; pop-up content and PDF files not fully reviewed; read-only (no page was changed).

## Comments
Page-by-page comments
Published content as of 10 October 2026 – evidence quoted verbatim from the live pages
# | Ref | Priority | Page(s) | Scope | Comment (what the published page shows) | Evidence (verbatim, as published 10 Oct 2026) | Proposed change | Decision owner (proposed) | Status
1 | F-01 | P1 | international_students ↔ admissions_requirements_cs_eng_majors | Linked from Admissions page | International CS/Engineering criteria still require SAT II (SAT Subject Tests were discontinued by College Board in 2021). | Intl: "Computer Science & Engineering Majors: Secondary School 40% / SAT I 30% / SAT II 30%" vs local "HS GPA ≥85 40% / Qudrat ≥65 30% / Tahseely ≥65 30%"; College Board ended Subject Tests (Jan 2021) | Replace with the approved alternative (e.g., SAT I / Tahseely equivalent) and remove SAT II. | Admissions + Colleges | Open – awaiting owner decision
2 | F-02 | P1 | international_students ↔ admission-from-other-universities, visiting-student-admission | Linked from Admissions page | International transfer/visiting application fee shows SAR 500 (excl. VAT), while transfer and visiting pages show SAR 950 (incl. VAT). | Intl: "SAR 500 (excl. VAT)"; local: "SAR 950 (incl. VAT)" | Publish one approved fee and VAT treatment per applicant type. | Finance + Admissions | Open – awaiting owner decision
3 | F-03 | P1 | college_of_medicine_admission (+ medical_program_studies_fees_tf_ro) | Linked from Admissions page | Medicine application fee: SAR 1,000 (incl. VAT) on the admission page vs SAR 1,150 (VAT inclusive) on the medical fees page. | Medicine: "SAR 1000 (incl. VAT)"; fees page: "Medical Application Fee SAR 1,150 (VAT inclusive)"; 1000×1.15=1150 | Confirm the approved amount and align both pages. | Finance + College of Medicine | Open – awaiting owner decision
4 | F-04 | P1 | admission_calendar_fs_ro | Linked from Admissions page | Admission calendar is for Fall 2026 only; all dates have passed and results are announced before some submission deadlines close. | "From July 19 to July 21, 2026" vs "Last day to submit IELTS or TOEFL iBT 2026-07-20"; all dates ≤ 2026-08-30; today 2026-10-10 | Publish the next intake (or 'Admissions closed – next intake opens on …') and fix date order. | Admissions | Open – awaiting owner decision
5 | F-16 | P1 | admissions_requirements_emgms_gdp | Linked from Admissions page | EMGMS page contains another university's text ('UA Center for English as Second Language (CESL)'). | "Graduate English Language Endorsement from UA Center for English as Second Language (CESL)"; "IELTS – minimum composite score of 7, with no subject area below a 6"; "TOEFL – minimum of 79 iBT" | Remove immediately and replace with PMU-approved EMGMS requirements. | Graduate Studies + College of Engineering | Open – awaiting owner decision
6 | F-48 | P1 | international_students ↔ admission_calendar_fs_ro | Linked from Admissions page | Non-Saudi applicants: calendar shows the Study in Saudi route as 'Closed' with no date, and the international page does not state the application route or deadline. | Calendar: "For non Saudi students: Apply online through Study in Saudi platform: https://studyinsaudi.sa/ar Closed" (no date); international page: "application process can be completed entirely online" (no route or deadline stated) | Publish the route and deadline for non-Saudi applicants on both pages. | Admissions | Open – awaiting owner decision
7 | F-06 | P2 | college_of_medicine_admission | Linked from Admissions page | Medicine: the published minimum components cannot reach the stated minimum total (0.2×95 + 0.4×80 + 0.4×80 = 83 < 86). | "(95%)","(80)","(80)" with "20% high school + 40% Qudrat + 40% Tahseely … 86 is the minimum": 0.2×95+0.4×80+0.4×80=83 | Clarify the minimums and formula. | College of Medicine + Admissions | Open – awaiting owner decision
8 | F-07 | P2 | undergraduate_programs_admission, admissions_requirements_cs_eng_majors | Linked from Admissions page | The minimum weighted total for admission is referred to but not published. | "the minimum weighted total, defined by the Admissions Office, should be met" | Decide whether to publish the minimum weighted total. | Admissions policy owner | Open – awaiting owner decision
9 | F-08 | P2 | toefl-admission, ielts-admission | Linked from Admissions page | TOEFL requirements are shown only on the 0–120 scale; ETS introduced the 1–6 reporting scale on 21 Jan 2026. | Core 83/19; ETS moved to 1–6 scale on 21 Jan 2026 (secondary source) | Publish an approved equivalence table including the new scale. | Admissions + Testing Center | Open – awaiting owner decision
10 | F-10 | P2 | direct-admissions…, admission-from-other-universities, cs_eng vs graduate pages | Linked from Admissions page | Undergraduate pages say 'equivalent TOEFL iBT' without a score, while graduate pages state 83/19. | "or equivalent TOEFL iBT (Learn more)" / "with acceptable scores" vs graduate "83 overall and 19 in each skill" | Publish one equivalence table and link it. | Admissions + Testing Center | Open – awaiting owner decision
11 | F-11 | P2 | admission (menu) ↔ admission_graduate_degree_programs ↔ degrees_programs_fs_ro | Linked from Admissions page | Graduate program lists differ between the hub menu, the graduate page and Degrees & Programs (MSHD vs MSEHD naming). | Menu lists EMGMS & MIBL; graduate home omits EMGMS; Degrees list omits EMGMS; labels "MSHD"/"MSEHD"/"Master of Human Development" | Maintain one graduate program catalogue. | Graduate Studies + Web | Open – awaiting owner decision
12 | F-13 | P2 | aptis-placement-test (+ student_fees_tf_ro) | Linked from Admissions page | The Aptis page does not state the test fee; the fees page shows SAR 575. | Aptis page: "they will be scheduled to take Aptis test"; fees page: "APTIS Exam Fees SAR 575" | Show the approved Aptis fee on the Aptis page. | PREP + Finance | Open – awaiting owner decision
13 | F-18 | P2 | all 39 scope items | Linked from Admissions page | Pages have an empty html 'lang' attribute (accessibility / screen readers). | document.documentElement.lang === "" on every www.pmu.edu.sa page probed (WCAG 3.1.1) | Set lang='en' / 'ar' appropriately. | Web / IT | Open – awaiting owner decision
14 | F-19 | P2 | all (main page: 4 of 6 images) | Linked from Admissions page | Images without alternative text (main page: 4 of 6). | main page images logo-name.png ×2, logo-PMU-1.png, logo_new_r.png have no alt attribute (WCAG 1.1.1) | Add alt text. | Web / IT | Open – awaiting owner decision
15 | F-22 | P2 | apply → admissions.pmu.edu.sa/welcome ↔ admission_calendar_fs_ro | Linked from Admissions page | Two conflicting calendars: the application portal shows 'No events are currently published' while the admission calendar shows Fall 2026 dates. | Portal: "No events are currently published. Please check back later."; site publishes dates; footer "2022 ©" | Use one calendar source. | Admissions + IT | Open – awaiting owner decision
16 | F-23 | P2 | apply | Linked from Admissions page | Bilingual requirements content on /apply is never seen: the page redirects immediately to the portal. | Static HTML of /apply has AR/EN IELTS/TOEFL text; browser lands on admissions.pmu.edu.sa/welcome with no requirements | Publish requirements on a visible page. | Admissions + Web | Open – awaiting owner decision
17 | F-25 | P2 | degrees_programs_fs_ro ↔ college_of_medicine_admission, emgms | Linked from Admissions page | Degrees & Programs does not list Medicine or EMGMS, although both have admission pages. | Rendered Degrees & Programs (10 tables) lacks Medicine & EMGMS; both have admission pages | Update the programme catalogue. | Admissions + Academic Affairs | Open – awaiting owner decision
18 | F-29 | P2 | admissions_requirements_milbl_gdp vs 21 graduate pages | Linked from Admissions page | MIBL requires IELTS 6.5, while other graduate pages require 6.0. | MIBL: "6.5 overall and 5.5 in each skill" vs others "6.0 overall and 5.5 in each skill" | Confirm the MIBL requirement. | Graduate Studies | Open – awaiting owner decision
19 | F-31 | P2 | admission_calendar_fs_ro (+ academic_calendar_2026_2027_ro) | Linked from Admissions page | Calendar: 'Orientation for new applicants – TBA'; no Spring window. | "Orientation for new applicants TBA" vs academic calendar "Orientation for the new students August 27, 2026"/"January 14, 2027" | Complete or remove; add next window. | Admissions | Open – awaiting owner decision
20 | F-32 | P2 | post_graduate_fees_tf_ro ↔ degrees_programs_fs_ro | Linked from Admissions page | Programmes priced on the graduate fees page (e.g., Master of Engineering in Innovation, Sustainability and Entrepreneurship) have no admission page or catalogue entry. | Fees list "Master of Engineering in Innovation, Sustainability, and Entrepreneurship (33)" and "PRE-Master for Master of Education"; no admission page or Degrees row | Confirm offering status and align. | Graduate Studies + Finance | Open – awaiting owner decision
21 | F-36 | P2 | admission (main page) | Linked from Admissions page | The main admission page consists mainly of link lists with little guidance. | Body = H1 "Admissions Office" + 4 H2 link lists; no intro, no intake status, no dates, no fees, no CTA hierarchy | Restructure around applicant type (journey). | Admissions + Web | Open – awaiting owner decision
22 | F-39 | P2 | 11 graduate menu targets | Linked from Admissions page | Graduate landing pages do not show the application fee or required documents. | 0 of 11 target pages contains "application fee" or "How to Apply"; these are on separate "Application Form" pages not linked from the main page | Add or link them. | Graduate Studies | Open – awaiting owner decision
23 | F-40 | P2 | college_of_medicine_admission | Linked from Admissions page | Medicine page uses non-standard wording and has no English-language requirement. | "the process typically involves understanding the weighting and criteria that the medical college uses…"; no IELTS/TOEFL/English requirement on page | Provide approved text including language requirement. | College of Medicine | Open – awaiting owner decision
24 | F-41 | P2 | direct-admissions…, graduate pages, toefl-admission, ielts-admission | Linked from Admissions page | 'IELTS 6.0 or TOEFL iBT 83' are not equivalent per ETS tables (6.0 ≈ 60–78; 83 ≈ 6.5). | PMU: "6.0 overall … or equivalent TOEFL iBT 83"; ETS: 6.0≈60–78 (67 newer table), 6.5≈79–93 (81) | Review the equivalence. | Admissions + Testing Center | Open – awaiting owner decision
25 | F-42 | P2 | admission-from-the-prep-to-ug-programs ↔ preparatory-program-study-plan | Linked from Admissions page | Preparatory maths placement matrix footnotes contradict between two pages. | "** Department of Architecture is excluded from PRPM 0012" yet Architecture row = PRPM 0012 "Yes"; IT footnote attached to Engineering/Architecture rows; study-plan page has different rows/footnotes | Keep one matrix. | PREP | Open – awaiting owner decision
26 | F-43 | P2 | admissions_requirements_milbl_gdp | Linked from Admissions page | MIBL: GPA requirement has no number and the 30% 'written test' is not described. | "A minimum (Very Good) in Bachelor’s Degree"; "30% for the written test" | Complete the requirements. | Graduate Studies | Open – awaiting owner decision
27 | F-45 | P2 | admissions_queries, admission_contact_gdp | Linked from Admissions page | Admission Query form collects name, email and mobile with no visible privacy notice; no phone channel. | Query form collects Name/Email/Mobile with no privacy text on page; graduate contact = "Office: G-017 Admin Bld; Email" only; undergrad "Contact Us" → staff directory | Add a privacy notice (legal review) and an official phone/email. | Admissions + Compliance | Open – awaiting owner decision
28 | F-47 | P2 | admissions_requirements_phdba_gdp | Linked from Admissions page | PhD BA: GPA rule unclear; accreditation claim (AACSB) not referenced. | "minimum cumulative GPA of 3.00 … or … 3.20"; "internationally accredited by AACSB as top 6%" (sources confirm membership, not full accreditation) | Clarify / reference. | Graduate Studies | Open – awaiting owner decision
29 | F-65 | P2 | admission page 'Contact Us' → faculty.pmu.edu.sa DepartmentStaffList/4 | Linked from Admissions page | 'Contact Us' leads to the Student Affairs staff list; no Admissions contact. | 15 entries; titles Registration/Career/Campus Life; none Admissions | Link to an Admissions contact page with official email/phone. | Admissions + Web | Open – awaiting owner decision
30 | F-68 | P2 | admissions_requirements_milbl_gdp vs application_form_milbl_gdp | Linked from Admissions page | MIBL contradicts itself: requirements page IELTS 6.5, application form page 6.0. | requirements: "6.5 overall and 5.5 in each skill"; application form: "6.0 overall and 5.5 in each skill" (both ... TOEFL iBT 83/19) | Confirm and align. | Graduate Studies | Open – awaiting owner decision
31 | F-69 | P2 | admissions_requirements_emgms_gdp | Linked from Admissions page | EMGMS: IELTS 7 vs TOEFL 79 (not equivalent) and legacy PBT test referenced. | "TOEFL – minimum of 79 iBT (or 60 on the revised PBT…)"; "IELTS – minimum composite score of 7…"; ETS: 79≈IELTS 6.5 | Replace with PMU-approved requirement. | Graduate Studies | Open – awaiting owner decision
32 | F-71 | P2 | apply → admissions.pmu.edu.sa/welcome | Linked from Admissions page | Bachelor's minimums and weights are published only on /apply, which redirects instantly (published minima compute to 72% non-engineering and 73% engineering/AI/CS). | Raw GET of /apply: meta refresh 0 + location.replace; body: non-eng HS80/Qudrat60, weights 60/40; Eng/AI/CS/Arch HS85/Qudrat65/Tahseely65, weights 40/30/30, SAT1 1200 alternative | Show requirements on a visible page; confirm the minimum weighted score. | Admissions | Open – awaiting owner decision
33 | F-72 | P2 | admissions_requirements_phdba_gdp | Linked from Admissions page | PhD BA eligibility sentence contains a double negative and three GPA thresholds without saying which applies. | "if the master degree is not from another discipline they must successfully attend and complete with minimum GPA 2.80 12 credit hours of MBA" | Rewrite as clear conditions. | Graduate Studies | Open – awaiting owner decision
34 | F-74 | P2 | admissions_requirements_emgms_gdp ↔ admission | Linked from Admissions page | EMGMS is listed on the hub but has no 'Apply' link or application route. | sidebar lists Apply for EMBA / MBA / MSHD / MSME only; hub lists 'Admissions to the EMGMS Program' | Add the route or state the programme status. | Graduate Studies + Web | Open – awaiting owner decision
35 | F-76 | P2 | /apply ↔ sat-admission ↔ admissions_requirements_cs_eng_majors | Linked from Admissions page | SAT 1200 alternative is described differently: /apply (instead of Qudrat and Tahseely, all Eng/AI/CS/Architecture), SAT page (international certificate holders, instead of Qudrat), CS/Eng page ('SAAT – Tahseely or SAT 1 (1200)'). | apply: "a SAT 1 total score of 1200 is accepted in place of both Qudrat and Tahseely"; sat-admission:56; cs_eng:89 | Publish one rule. | Admissions | Open – awaiting owner decision
36 | F-14 | P3 | multiple | Linked from Admissions page | Spelling/wording errors (e.g., 'Visting Students', 'wave' for 'waive', 'Verifaction Code'). | "Visting Students","wave one or more","Verifaction Code","College of Medical","ADMISSSIONS"×4,"Admisssions"×2 | Proofread. | Admissions + Web | Open – awaiting owner decision
37 | F-20 | P3 | all | Linked from Admissions page | No meta description/canonical; several hosts/URL forms for the same page. | Main page served at pmu.edu.sa without redirect to www; links use "../Admission/X.aspx" (legacy case/extension) | Set canonical URLs. | Web / IT | Open – awaiting owner decision
38 | F-24 | P3 | admission_calendar_fs_ro | Linked from Admissions page | Calendar 'Apply Now' uses javascript:__doPostBack instead of a normal link. | href="javascript:WebForm_DoPostBackWithOptions(… Apply_Now_ADS …)"; 7 URL forms reach the same portal | Use a standard link. | Web / IT | Open – awaiting owner decision
39 | F-26 | P3 | undergraduate_programs_admission, international_students, calendar | Linked from Admissions page | Heading levels out of order on several pages. | H2 before H1; H1→H3→H4 then H3; H2→H4 | Fix heading order. | Web / IT | Open – awaiting owner decision
40 | F-35 | P3 | sat-admission ↔ admissions_requirements_cs_eng_majors | Linked from Admissions page | The list of majors with higher requirements differs between the SAT page and the CS/Engineering page. | SAT page lists "Artificial Intelligence … etc."; CS/Eng page omits AI & Cybersecurity | Publish one list. | Admissions | Open – awaiting owner decision
41 | F-37 | P3 | admission; admission_graduate_degree_programs | Linked from Admissions page | Ambiguous/duplicated link labels (e.g., several 'Home'). | "Home"×3 (3 different targets); "Tuition & Fees"×2 (different targets); "Application Form"/"Admissions Requirements"×5 identical | Use unique labels. | Web | Open – awaiting owner decision
42 | F-38 | P3 | admission (main page) | Linked from Admissions page | Structural accessibility issues on the main page (empty link, landmarks). | No <main> landmark (HEADER,NAV,HEADER,NAV,FOOTER,FOOTER); empty anchor href="#sidebar"; iframe search/new-search.html has no title; logo-PMU-1.png 301 (case) | Fix structure. | Web / IT | Open – awaiting owner decision
43 | F-44 | P3 | aptis-placement-test | Linked from Admissions page | Aptis score bands are not published; 'Core Program' term unexplained. | Levels listed (Pre Beginner…Advanced) without score bands; "direct entry into the Core Program" | Publish bands. | PREP | Open – awaiting owner decision
44 | F-46 | P3 | international_students | Linked from Admissions page | International page: empty 'Transportation' section; 'Acceptable SAT I' with no score. | "Transportation" heading with no text; "Acceptable SAT I" (no threshold) vs 1200/1300 elsewhere | Complete or remove. | Admissions | Open – awaiting owner decision
45 | F-49 | P3 | admission_calendar_fs_ro | Linked from Admissions page | Calendar blocks are duplicated in the page source. | Rendered text repeats Undergraduate and Graduate calendar blocks twice | Remove duplication. | Web | Open – awaiting owner decision
46 | F-66 | P3 | Staff_List?DEpt=4&Name=Staff Name | Linked from Admissions page | Duplicated staff entry; placeholder parameter 'Name=Staff Name' in the link. | duplicate entry; Name=Staff Name dropped on redirect | Clean up. | Web | Open – awaiting owner decision
47 | F-67 | P3 | /default | Linked from Admissions page | Home page shows the NCAAA paragraph twice (visible, mobile). | Mobile DOM probe (390px): the NCAAA paragraph appears twice, both visible, not inside a slider; lang attr empty; no <h1> | Remove duplicate. | Web | Open – awaiting owner decision
48 | F-70 | P3 | /default | Linked from Admissions page | Home page has no lang attribute and no H1. | result8_home.json: lang="", h1=[] | Add. | Web / IT | Open – awaiting owner decision
49 | F-73 | P3 | admissions_requirements_emba_gdp | Linked from Admissions page | EMBA: 'from three to five years of professional work experience' implies a maximum. | "Successful candidates should have from three to five years of professional work experience" | State the minimum only (if intended). | Graduate Studies | Open – awaiting owner decision
50 | F-75 | P3 | application_form_deme_gdp | Linked from Admissions page | PhD Mechanical Engineering page title says 'Application Form for MSDH'. | TITLE: Application Form for MSDH :: Graduate Degree Programs … ; H: PhD in Mechanical Engineering ADMISSSIONS REQUIREMENTS | Correct the page title. | Web | Open – awaiting owner decision
51 | F-77 | P3 | admissions.pmu.edu.sa/welcome | Linked from Admissions page | Application portal is English-only, shows no privacy link and no admission calendar. | Browser probe 2026-10-10: lang=en; privacy links=0; 'No events are currently published' (prior observation) | Add Arabic and privacy notice (after compliance review). | Admissions + IT | Open – awaiting owner decision
52 | F-17 | P1 | freshman_admission (orphan) | Legacy/adjacent page (not linked from hub) | Legacy page 'freshman_admission' (not linked from the hub) still shows old weights (30/50/20) and exemptions. | "High school 30% / Aptitude Test 50% / Personal Interview 20%"; "TOEFL … 513 (CBT 183, iBT 65)" | Redirect or unpublish. | Admissions + Web | Open – awaiting owner decision
53 | F-27 | P1 | payment_schedule_tf_ro_fall; faq_tf_ro | Legacy/adjacent page (not linked from hub) | Payment schedule and fees FAQ still show 2025/26 fees. | 10,000+10,000+9,000=29,000 vs 2026/27 "SAR 30,000 / semester" | Update or archive. | Finance | Open – awaiting owner decision
54 | F-05 | P2 | transfer-student-admission (orphan) | Legacy/adjacent page (not linked from hub) | Legacy transfer page states IELTS 5.0 per skill. | "minimum score of 5.0 on each test component" | Redirect or unpublish. | Admissions + Web | Open – awaiting owner decision
55 | F-09 | P2 | ielts_course (orphan) | Legacy/adjacent page (not linked from hub) | 2019 IELTS course page still online. | "From July 14, 2019 to August 02, 2019" | Archive. | Web | Open – awaiting owner decision
56 | F-21 | P2 | next-steps | Legacy/adjacent page (not linked from hub) | 'Next steps' page scrolls horizontally on mobile (440 > 390 px). | scrollWidth 440 vs 390 | Fix layout. | Web / IT | Open – awaiting owner decision
57 | F-28 | P2 | payment_method_tf_ro | Legacy/adjacent page (not linked from hub) | Refund policy statements contradict on the payment method page. | "All tuition payments are non-refundable." + 25%/50%/75% deductions | Clarify. | Finance | Open – awaiting owner decision
58 | F-30 | P2 | sidebar targets (scholarships, GPA calculator) | Legacy/adjacent page (not linked from hub) | Four sidebar links return 404; financial aid page empty. | 404 - File or directory not found | Fix links. | Web | Open – awaiting owner decision
59 | F-15 | P3 | news/2010; news?ID=1115 | Legacy/adjacent page (not linked from hub) | Old news items (2010, 1435/1436H) still reachable. | "العام الجامعي 1436/1435هـ" | Archive. | Web | Open – awaiting owner decision
60 | F-33 | P3 | 13 academic calendars; PDFs | Legacy/adjacent page (not linked from hub) | 13 generations of academic calendars and old PDFs online. | calendars 2014/15→2026/27; Aptis guide PDF created 2017 | Archive. | Registrar + Web | Open – awaiting owner decision
61 | F-34 | P3 | registration_office | Legacy/adjacent page (not linked from hub) | Link to an internal host (http://web1:8066/...) on a public page. | http://web1:8066/Online_Room_Reservation_Form.aspx | Remove. | IT | Open – awaiting owner decision

## Decisions
Decisions required
Values pending these decisions should not be published as policy until confirmed in writing by the owner
ID | Decision needed | Owner (proposed) | Linked refs | Priority
D-01 | Next intake and one application route per applicant type (Saudi / non-Saudi / transfer / visiting / graduate); publish requirements on a visible page | Admissions + Web + IT | F-04, F-22, F-23, F-48, F-71 | P1
D-02 | Fee & VAT matrix: international transfer/visitor (500 excl. vs 950 incl.), Medicine (1,000 vs 1,150), Aptis (575; requested 950) | Finance + Admissions + PREP | F-02, F-03, F-13 | P1
D-03 | Minimum weighted scores (74% requested vs published minima giving 73% / 72%) and whether to publish them | Admissions policy owner | F-07, F-71 | P1
D-04 | Criteria for international CS/Engineering applicants replacing SAT II; scope of SAT 1200 alternative; list of majors with higher requirements (incl. AI?) | Admissions + Colleges | F-01, F-35, F-76 | P1
D-05 | Graduate English requirements: MIBL 6.0 vs 6.5; EMGMS (remove other university text, IELTS 7/TOEFL 79/PBT); application route for EMGMS | Graduate Studies + College of Engineering | F-16, F-29, F-68, F-69, F-74 | P1
D-06 | TOEFL/IELTS equivalence table incl. the TOEFL 1–6 scale | Admissions + Testing Center | F-08, F-10, F-41 | P2
D-07 | Medicine selection formula and minimums; language requirement | College of Medicine + Admissions | F-06, F-40 | P2
D-08 | Graduate catalogue: offered programmes and canonical pages (MSHD/MSEHD, Innovation & Sustainability programme) | Graduate Studies + Academic Affairs | F-11, F-25, F-32, F-75 | P2
D-09 | Admissions contact channel and privacy notice on query form / portal | Admissions + Compliance | F-45, F-65, F-77 | P2
D-10 | Retire/redirect legacy pages (freshman_admission, transfer-student-admission, ielts_course, old calendars/news) | Admissions + Web | F-05, F-09, F-15, F-17, F-33 | P2

## Previous requests
Previous requests – live status
Amendments requested in the thread "comments on Admission pages", re-checked against the live site on 10 October 2026
Requested (Oct 2025 / Feb 2026 thread) | Live today (10 Oct 2026) | Status
B.S. Chemical Engineering added | Listed on Degrees & Programs | Implemented
Minimum weighted score 74% (CS/Eng) / 72% (others) | Not stated on visible pages; published minima on /apply compute to 73% / 72% | Not implemented – decision needed
International / transfer / visitor fee to SAR 950 | International page still SAR 500 (excl. VAT); transfer & visiting pages SAR 950 (incl. VAT) | Partially – VAT wording to confirm
Remove SAT II (CS & Engineering) | International page still shows SAT II 30% | Not implemented
Aptis re-test fee SAR 950 | Fees page SAR 575; Aptis page shows no fee | Not implemented / amount to confirm
Retire old CS/Engineering page and Web Admission Guide | CS/Engineering requirements page still live; guide not verifiable | Not implemented / not verifiable
Graphic Design – female only | Degrees & Programs shows Male and Female | Not implemented – confirm
Admission data-flow (Feb 2026 draft) | Not published | Draft – not verifiable